## Sheet1
| System Name: | GALA | Status:
| Members: | A. Lacanglacang | To-do
|  | B. Magno | In-progress
|  | C.Paden | Done
|  |  | On hold |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
| ACTIVITIES | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Create and Submit a Gantt Chart Draft | A. Lacanglacang |  |  | Done
2 | Create and Submit a Functional Requirement Document | B. Magno |  |  | Done
3 | Finalize the Gantt Chart and the Functional Requirement Document | C.Paden |  |  | Done
4 | Start brainstorming for the theme, aesthethic and appearance of the app | A, B, C |  |  | Done
5 | Draft for the app loading screen and log-in/sign-in page | A, B, C |  |  | Done
6 | Assigning of the functionalities for figma | A, B, C |  |  | Done
7 | Draft for the figma app (all of the functionalities available) | A, B, C |  |  | Done
8 | Revisions for the document version 2.0 | A, B, C |  |  | Done
9 | Finalization of the functionalities of our application system in figma app | A, B, C |  |  | Done
10 | Revisions and adjustments for the functionalities and layout | A, B, C |  |  | On hold
11 | Discussion for the version 3.0 of our document | A, B, C |  |  | Done
12 | Coding for the functionalities of the assigned layouts | A, B, C |  |  | In-progress
13 | Revisions for the document at the end of the month | A, B, C |  |  | To-do